## Workplan
Activity ID | Activity/Task | Description | Output Link | Responsible | Start Date | End Date | Duration (Days) | Dependencies | Status | % Complete | Budget Allocated | Budget Spent | Notes
| OUTPUT 1: SLM Capacity Assessments Completed |  | Output 1
1.1 | Activity 1.1: Design Assessment Methodology |  | Output 1
1.1.1 | Conduct literature review of SLM capacity frameworks | Review existing capacity assessment methodologies | Output 1 | Technical Advisor | 2026-04-01 | 2026-04-15 |  |  | Not Started | 0 | 5000 | 0
1.1.2 | Develop assessment tools and questionnaires | Design data collection instruments | Output 1 | M&E Officer | 2026-04-15 | 2026-04-30 |  | 1.1.1 | Not Started | 0 | 3000 | 0
1.1.3 | Pilot test methodology in one country | Field test and validate tools | Output 1 | Technical Advisor | 2026-05-01 | 2026-05-15 |  | 1.1.2 | Not Started | 0 | 8000 | 0
1.2 | Activity 1.2: Conduct Country Assessments |  | Output 1
1.2.1 | Stakeholder mapping in target countries | Identify and categorise key stakeholders | Output 1 | Programme Officer | 2026-05-15 | 2026-06-15 |  | 1.1.3 | Not Started | 0 | 4000 | 0
1.2.2 | Conduct assessment missions (5 countries) | In-country data collection and consultations | Output 1 | Assessment Team | 2026-06-15 | 2026-08-31 |  | 1.2.1 | Not Started | 0 | 25000 | 0
1.2.3 | Analyse findings and draft reports | Data analysis and report writing | Output 1 | Technical Advisor | 2026-09-01 | 2026-09-30 |  | 1.2.2 | Not Started | 0 | 6000 | 0
1.3 | Activity 1.3: Validate and Disseminate Results |  | Output 1
1.3.1 | Conduct validation workshops in each country | Present findings for stakeholder feedback | Output 1 | Programme Manager | 2026-10-01 | 2026-10-31 |  | 1.2.3 | Not Started | 0 | 10000 | 0
1.3.2 | Finalise and publish assessment reports | Incorporate feedback and publish | Output 1 | Communications Officer | 2026-11-01 | 2026-11-30 |  | 1.3.1 | Not Started | 0 | 4000 | 0
| OUTPUT 2: SLM Training Programme Delivered |  | Output 2
2.1 | Activity 2.1: Develop Training Curriculum |  | Output 2
2.1.1 | Review training needs from assessments | Analyse assessment data for training priorities | Output 2 | Training Specialist | 2026-07-01 | 2026-07-15 |  | 1.2.2 | Not Started | 0 | 3000 | 0
2.1.2 | Design curriculum and training materials | Develop modular training programme | Output 2 | Training Specialist | 2026-07-15 | 2026-08-31 |  | 2.1.1 | Not Started | 0 | 8000 | 0
2.1.3 | Peer review and approval of curriculum | Technical committee review | Output 2 | Programme Director | 2026-09-01 | 2026-09-15 |  | 2.1.2 | Not Started | 0 | 1000 | 0
2.2 | Activity 2.2: Deliver Training Workshops |  | Output 2
2.2.1 | Recruit and brief facilitators | Engage training facilitators | Output 2 | HR / Procurement | 2026-09-15 | 2026-10-01 |  | 2.1.3 | Not Started | 0 | 5000 | 0
2.2.2 | Conduct national training workshops (5 countries) | Deliver training to 100 officers | Output 2 | Training Specialist | 2026-10-01 | 2026-12-15 |  | 2.2.1 | Not Started | 0 | 35000 | 0
2.2.3 | Post-training follow-up and mentoring | Support application of learning | Output 2 | Training Specialist | 2027-01-01 | 2027-03-31 |  | 2.2.2 | Not Started | 0 | 10000 | 0
| OUTPUT 3: Knowledge Platform Established |  | Output 3
3.1 | Activity 3.1: Design and Build Platform |  | Output 3
3.1.1 | Define platform requirements and specifications | User requirements gathering | Output 3 | IT Specialist | 2026-05-01 | 2026-05-31 |  |  | Not Started | 0 | 3000 | 0
3.1.2 | Develop and test platform | Platform development and QA | Output 3 | IT Specialist | 2026-06-01 | 2026-08-31 |  | 3.1.1 | Not Started | 0 | 20000 | 0
3.1.3 | User acceptance testing | Test with sample users | Output 3 | M&E Officer | 2026-09-01 | 2026-09-15 |  | 3.1.2 | Not Started | 0 | 2000 | 0
3.2 | Activity 3.2: Launch and Populate Platform |  | Output 3
3.2.1 | Curate and upload initial content | Populate with existing resources | Output 3 | Communications Officer | 2026-09-15 | 2026-10-31 |  | 3.1.3 | Not Started | 0 | 4000 | 0
3.2.2 | Platform launch events in each country | National launch and user training | Output 3 | Programme Manager | 2026-11-01 | 2026-12-15 |  | 3.2.1 | Not Started | 0 | 12000 | 0
3.2.3 | Ongoing content management and moderation | Regular updates and user support | Output 3 | Communications Officer | 2027-01-01 | 2027-03-31 |  | 3.2.2 | Not Started | 0 | 6000 | 0

## Milestone Tracker
Milestone # | Description | Target Date | Actual Date | Status | Evidence | Notes
MS-01 | Programme inception completed | 2026-04-15 |  | Not Started |  | Inception report approved
MS-02 | Assessment methodology finalised | 2026-04-30 |  | Not Started
MS-03 | Assessment tools piloted and validated | 2026-05-15 |  | Not Started
MS-04 | Stakeholder mapping completed (all countries) | 2026-06-15 |  | Not Started
MS-05 | Knowledge platform requirements defined | 2026-05-31 |  | Not Started
MS-06 | Country assessments completed (5 countries) | 2026-08-31 |  | Not Started
MS-07 | Knowledge platform developed and tested | 2026-09-15 |  | Not Started
MS-08 | Training curriculum approved | 2026-09-15 |  | Not Started
MS-09 | Assessment validation workshops completed | 2026-10-31 |  | Not Started
MS-10 | Assessment reports published | 2026-11-30 |  | Not Started
MS-11 | Training workshops completed (all countries) | 2026-12-15 |  | Not Started
MS-12 | Knowledge platform launched | 2026-12-15 |  | Not Started
MS-13 | Post-training mentoring completed | 2027-03-31 |  | Not Started
MS-14 | Mid-term review completed | 2026-10-31 |  | Not Started
MS-15 | Programme completion and final evaluation | 2027-03-31 |  | Not Started

## Gantt Chart
ID | Activity | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027
OUTPUT 1: SLM Capacity Assessments
1.1 | Design Assessment Methodology
1.2 | Conduct Country Assessments
1.3 | Validate and Disseminate Results
OUTPUT 2: SLM Training Programme
2.1 | Develop Training Curriculum
2.2 | Deliver Training Workshops
OUTPUT 3: Knowledge Platform
3.1 | Design and Build Platform
3.2 | Launch and Populate Platform
Legend: | Output 1 | Output 2 | Output 3

## Instructions
Instructions
PROGRAMME WORKPLAN TEMPLATE — Usage Guide
1. Use the Workplan sheet to detail all programme activities and tasks.
2. Organise activities under their parent Outputs.
3. Use hierarchical numbering (1.1, 1.1.1) for activities and tasks.
4. Set realistic start and end dates; Duration calculates automatically.
5. Document Dependencies to show task relationships.
6. Update Status and % Complete regularly.
7. Track budget allocation and spending per activity.
8. Use the Milestone Tracker to monitor key programme milestones.
9. The Gantt Chart provides a visual timeline overview.
Tips:
- Review and update the workplan monthly.
- Flag delays early and document reasons.
- Align milestones with donor reporting requirements.
- Use the workplan as the basis for progress reporting.
This template follows Verified Global's Implementation Totality methodology.