Programme Progress Report

________________________________________

Programme Name:  [Enter Programme Name]

Reporting Period:  [DD/MM/YYYY] to [DD/MM/YYYY]

Report Date:  [DD/MM/YYYY]

Prepared By:  [Name and Title]

Organisation:  [Organisation Name]

Verified Global

Implementation Totality

TABLE OF CONTENTS

[Auto-generated — Update field codes after editing in Word: select all (Ctrl+A) then press F9]

1. Executive Summary

2. Programme Overview

3. Progress Against Workplan

4. Financial Summary

5. Risk and Issues Log

6. Stakeholder Engagement

7. Lessons Learned

8. Next Period Plan

9. Annexes

1. Executive Summary

Status Overview

| Dimension | Status (RAG) | Comments |
| --- | --- | --- |
| Overall Status | [Green / Amber / Red] | [Brief commentary] |
| Budget Status | [Green / Amber / Red] | [Brief commentary] |
| Timeline Status | [Green / Amber / Red] | [Brief commentary] |
| Risk Level | [High / Medium / Low] | [Brief commentary] |

Key Achievements This Period

- Successfully completed stakeholder consultation workshop with 45 participants across 6 SIDS

- Finalised baseline assessment report for sustainable land management indicators

- Procurement of technical equipment completed on schedule and within budget

Key Challenges

- Delayed receipt of co-financing commitment letter from [Partner Organisation]

- Staff turnover in national implementing agency requiring additional capacity building

- Adverse weather conditions affecting field data collection in Q2

Critical Decisions Required

- [Decision 1: e.g., Approval of revised workplan for Output 3]

- [Decision 2: e.g., Budget reallocation from Travel to Consultancies]

- [Decision 3: e.g., Extension of subcontract for technical specialist]

2. Programme Overview

| Field | Details |
| --- | --- |
| Programme Name | [Full Programme Title] |
| Funder | [e.g., Global Environment Facility (GEF)] |
| Implementing Agency | [e.g., United Nations Environment Programme (UNEP)] |
| Start Date | [DD/MM/YYYY] |
| End Date | [DD/MM/YYYY] |
| Total Budget | [USD X,XXX,XXX] |
| Budget Utilised to Date | [USD X,XXX,XXX] ([XX]%) |
| Programme Manager | [Name] |

3. Progress Against Workplan

| Output / Activity | Planned Milestone | Status | % Complete | Comments |
| --- | --- | --- | --- | --- |
| Output 1: Institutional Framework Strengthened |  |  |  |  |
| 1.1 Stakeholder mapping | Complete by Q1 | Completed | 100% | Report submitted |
| 1.2 Capacity needs assessment | Complete by Q2 | On Track | 75% | Draft under review |
| 1.3 Training programme design | Complete by Q3 | Not Started | 0% | Dependent on 1.2 |
| Output 2: SLM Practices Demonstrated |  |  |  |  |
| 2.1 Site selection and baseline | Complete by Q1 | Completed | 100% | 5 sites selected |
| 2.2 Demonstration plot establishment | Complete by Q2 | Delayed | 40% | Weather delays |
| 2.3 Farmer training workshops | Complete by Q3 | On Track | 60% | 3 of 5 completed |
| Output 3: Knowledge Management System |  |  |  |  |
| 3.1 KM platform design | Complete by Q2 | On Track | 80% | Beta testing phase |
| 3.2 Content development | Complete by Q3 | On Track | 50% | Case studies drafted |
| 3.3 Dissemination strategy | Complete by Q4 | Not Started | 0% | Planned for Q4 |

4. Financial Summary

| Budget Category | Annual Budget (USD) | Expenditure This Period | Cumulative Expenditure | Balance | % Utilised |
| --- | --- | --- | --- | --- | --- |
| Personnel | 250,000 | 62,500 | 187,500 | 62,500 | 75% |
| Travel | 80,000 | 15,200 | 48,600 | 31,400 | 61% |
| Equipment | 120,000 | 0 | 115,000 | 5,000 | 96% |
| Training | 60,000 | 18,000 | 36,000 | 24,000 | 60% |
| Consultancies | 150,000 | 35,000 | 95,000 | 55,000 | 63% |
| Operating Costs | 40,000 | 10,000 | 28,000 | 12,000 | 70% |
| Contingency | 30,000 | 0 | 5,000 | 25,000 | 17% |
| TOTAL | 730,000 | 140,700 | 515,100 | 214,900 | 71% |

5. Risk and Issues Log

| Risk / Issue | Type | Severity | Mitigation / Resolution | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| Co-financing delays from partner agency | Risk | High | Escalate to Steering Committee; identify interim funding | PM | Open |
| Staff turnover in implementing agency | Issue | High | Recruit replacement; provide accelerated onboarding | NPC | In Progress |
| Climate events disrupting field activities | Risk | Medium | Build weather contingency into workplan; identify alternative sites | Field Lead | Monitoring |
| Procurement delays for laboratory equipment | Issue | Medium | Expedite with procurement unit; consider alternative suppliers | Procurement | Resolved |
| Low stakeholder engagement in remote communities | Risk | Low | Engage community leaders; use local language materials | Comms Officer | Monitoring |

6. Stakeholder Engagement

Engagement Activities This Period

- National Steering Committee meeting held on [date] — key decisions documented in Annex C

- Community consultation sessions conducted in [locations] with [number] participants

- Technical working group session on M&E framework finalisation

- Bilateral meeting with [Partner Organisation] regarding co-financing commitments

Upcoming Engagement Planned

- Regional knowledge exchange workshop — [date and location]

- Donor site visit — [date]

- Annual project review meeting — [date]

7. Lessons Learned

| Lesson | Context | Recommendation | Applied |
| --- | --- | --- | --- |
| Early stakeholder engagement reduces implementation resistance | Community push-back on site selection was mitigated by inclusive consultation | Begin stakeholder mapping and engagement in inception phase | Yes |
| Flexible procurement processes are essential in SIDS contexts | Limited local suppliers caused delays in equipment procurement | Pre-qualify international suppliers; build longer lead times into workplan | In Progress |
| Digital tools improve M&E data quality and timeliness | Paper-based data collection led to errors and delays | Adopt mobile data collection tools (e.g., KoboToolbox) from project start | Yes |

8. Next Period Plan

| Priority | Activity | Expected Outcome | Timeline | Responsible |
| --- | --- | --- | --- | --- |
| 1 | Complete capacity needs assessment report | Finalised report approved by Steering Committee | Month 1 | National Consultant |
| 2 | Establish remaining demonstration plots | All 5 sites operational with baseline data | Months 1-2 | Field Team Lead |
| 3 | Launch KM platform beta | Platform live with initial content for user testing | Month 2 | IT Consultant |
| 4 | Conduct mid-term financial review | Updated budget forecast and reallocation proposal | Month 2 | Finance Officer |
| 5 | Prepare for mid-term evaluation | ToR drafted and evaluation team recruited | Month 3 | Programme Manager |

9. Annexes

Annex A: Detailed Financial Statement

[Attach detailed financial statement with line-item breakdown]

Annex B: Updated Risk Register

[Attach full risk register with probability and impact assessments]

Annex C: Meeting Minutes

[Attach minutes from Steering Committee and key meetings held during the reporting period]