## Risk Register
Risk ID | Date Identified | Category | Description | Root Cause | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Mitigation Strategy | Contingency Plan | Owner | Status | Review Date | Notes
RSK-001 | 2026-01-15 | Financial | Budget overrun due to currency fluctuation or underestimated costs | Inadequate cost estimation or exchange rate volatility | 4 | 4 |  |  | Monthly budget reviews; contingency fund of 10% | Request supplementary funding from donor | Finance Officer | Open | 2026-04-15
RSK-002 | 2026-01-15 | Strategic | Key stakeholder disengagement from programme activities | Competing priorities or insufficient communication | 3 | 5 |  |  | Regular stakeholder engagement meetings; progress dashboards | Escalate to Programme Steering Committee | Programme Manager | Mitigating | 2026-04-15
RSK-003 | 2026-01-15 | Operational | High staff turnover in implementing agency | Uncompetitive salaries or poor working conditions | 3 | 4 |  |  | Knowledge management system; cross-training staff | Engage short-term consultants to fill gaps | HR Lead | Open | 2026-04-15
RSK-004 | 2026-01-15 | Strategic | Scope creep expanding beyond original programme design | Unclear boundaries or stakeholder pressure for additions | 4 | 3 |  |  | Strict change control process; baseline documentation | Formal scope review and renegotiation with donor | Programme Director | Open | 2026-04-15
RSK-005 | 2026-01-15 | External | Regulatory or policy changes affecting programme delivery | Government transition or new legislation | 2 | 5 |  |  | Monitor policy landscape; maintain government relationships | Adapt programme design to new regulatory context | Policy Advisor | Open | 2026-07-15
RSK-006 | 2026-01-15 | Operational | Procurement delays impacting activity timelines | Complex procurement procedures or limited vendor pool | 4 | 3 |  |  | Early procurement planning; pre-qualified vendor lists | Direct contracting for urgent items with donor approval | Procurement Officer | Mitigating | 2026-04-15
RSK-007 | 2026-01-15 | Technical | Poor data quality undermining M&E reporting | Inadequate data collection tools or untrained staff | 3 | 4 |  |  | Data quality assessments; standardised collection tools | Engage M&E specialist for data cleaning exercise | M&E Officer | Open | 2026-04-15
RSK-008 | 2026-01-15 | Technical | Technology systems failure disrupting operations | Outdated infrastructure or lack of backup systems | 2 | 4 |  |  | Regular backups; IT maintenance schedule; cloud-based systems | Activate business continuity plan; manual processes | IT Coordinator | Open | 2026-07-15

## Risk Matrix
RISK MATRIX
Likelihood ↓ / Impact → | 1 - Negligible | 2 - Minor | 3 - Moderate | 4 - Major | 5 - Severe
5 - Almost Certain | 5 | 10 | 15 | 20 | 25
4 - Likely | 4 | 8 | 12 | 16 | 20
3 - Possible | 3 | 6 | 9 | 12 | 15
2 - Unlikely | 2 | 4 | 6 | 8 | 10
1 - Rare | 1 | 2 | 3 | 4 | 5
Legend:
Critical (15-25)
High (10-14)
Medium (5-9)
Low (1-4)

## Instructions
Instructions
RISK REGISTER TEMPLATE — Usage Guide
1. Use the Risk Register sheet to log all identified programme risks.
2. Assign each risk a unique ID (RSK-001, RSK-002, etc.).
3. Select the Category from the dropdown list.
4. Score Likelihood and Impact from 1 (lowest) to 5 (highest).
5. The Risk Score and Risk Level are calculated automatically.
6. Document clear Mitigation Strategies and Contingency Plans.
7. Assign an Owner responsible for monitoring each risk.
8. Update Status regularly using the dropdown (Open/Mitigating/Escalated/Closed).
9. Set Review Dates and conduct periodic risk reviews.
10. Refer to the Risk Matrix sheet for visual risk prioritisation.
Risk Level Thresholds:
- Critical: Score 15–25 — Immediate action required
- High: Score 10–14 — Urgent attention needed
- Medium: Score 5–9 — Monitor closely
- Low: Score 1–4 — Monitor periodically
This template follows Verified Global's Quality Stress Testing methodology.