## Stakeholder Register
ID | Stakeholder Name | Organisation | Role/Title | Stakeholder Type | Influence Level (1-5) | Interest Level (1-5) | Engagement Priority | Current Engagement | Desired Engagement | Engagement Strategy | Communication Channel | Communication Frequency | Key Concerns/Interests | Risks if Not Engaged | Notes
SH-001 | Programme Director | Implementing Agency | Director | Internal | 5 | 5 |  | Champion | Champion | Regular briefings; inclusion in all decisions | Email / Meetings | Weekly | Programme delivery; accountability to donors | Loss of programme oversight and direction
SH-002 | Finance Officer | Implementing Agency | Senior Finance Officer | Internal | 3 | 4 |  | Supportive | Champion | Monthly financial reviews; capacity building | Email / Reports | Monthly | Budget compliance; audit readiness | Financial mismanagement; audit findings
SH-003 | Minister of Environment | Government | Minister | External | 5 | 3 |  | Neutral | Supportive | Quarterly briefings; invite to key events | Formal correspondence | Quarterly | Political visibility; national priorities | Loss of political support; policy misalignment
SH-004 | Community Leader | Local Community | Village Chief | Beneficiary | 2 | 5 |  | Neutral | Supportive | Community meetings; participatory planning | Face-to-face / Phone | Monthly | Community benefits; local employment | Community resistance; project delays
SH-005 | Donor Representative | GEF / World Bank | Task Team Leader | Funder | 5 | 5 |  | Supportive | Champion | Quarterly progress reports; supervision missions | Email / Video calls | Quarterly | Results delivery; fiduciary compliance | Funding suspension; negative evaluation
SH-006 | Technical Advisor | Partner Agency | Senior Specialist | Partner | 4 | 4 |  | Supportive | Champion | Technical working group; co-design sessions | Email / Workshops | Fortnightly | Technical quality; knowledge sharing | Poor technical outcomes; duplication
SH-007 | Media Contact | National Newspaper | Editor | External | 3 | 2 |  | Unaware | Supportive | Press releases; media events at milestones | Email / Press packs | As needed | Newsworthy stories; public interest | Negative or no media coverage
SH-008 | Contractor | Construction Firm | Project Manager | Partner | 2 | 3 |  | Neutral | Supportive | Clear ToR; regular supervision; payment schedule | Meetings / Site visits | Weekly | Timely payment; clear specifications | Delays; quality issues; disputes
SH-009 | Regulatory Body | Environmental Agency | Director | Regulator | 4 | 3 |  | Neutral | Supportive | Compliance reports; early consultation on permits | Formal correspondence | Quarterly | Environmental compliance; permit adherence | Permit refusal; compliance penalties
SH-010 | Beneficiary Group | Farmers Association | Chairperson | Beneficiary | 2 | 5 |  | Resistant | Supportive | Participatory assessments; demonstration sites | Community meetings | Monthly | Livelihood improvement; land tenure | Non-adoption; programme irrelevance

## Power-Interest Grid
POWER-INTEREST GRID
| Low Interest | High Interest
High Power | KEEP SATISFIED Monitor needs; Provide information | MANAGE CLOSELY Active engagement; Key decision-makers
Low Power | MONITOR Minimal effort; Keep aware | KEEP INFORMED Regular updates; Consultation

## Engagement Action Plan
Stakeholder | Action | Responsible Person | Timeline | Status

## Instructions
Instructions
STAKEHOLDER ANALYSIS MATRIX — Usage Guide
1. List all programme stakeholders in the Stakeholder Register.
2. Assess each stakeholder's Influence (power to affect the programme) and Interest (concern about the programme) on a 1–5 scale.
3. Engagement Priority is calculated automatically (Influence × Interest).
4. Use the Power-Interest Grid to categorise stakeholders into quadrants.
5. Define engagement strategies based on quadrant placement.
6. Track actions in the Engagement Action Plan sheet.
7. Review and update quarterly or when significant changes occur.
Engagement Levels:
Unaware — Does not know about the programme
Resistant — Aware but opposed or disengaged
Neutral — Aware but neither supportive nor resistant
Supportive — Actively supports the programme
Champion — Advocates for the programme proactively